## Sheet1
S. No | Task Name | Start Date | End Date | Status | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
1 | Topic Selection | 2025-07-03 | 2025-07-17 | Completed
2 | Zeroth Review | 2025-07-18 | 2025-07-19 | Completed
2.1 | Presentation Preparation | 2025-07-18 | 2025-07-19 | Completed
3 | Literature Survey | 2025-07-30 | 2025-09-09 | Completed
3.1 | Collection and analysis of research papers | 2025-07-30 | 2025-08-21 | Completed
3.2 | Preparation for literature survey presentation | 2025-08-22 | 2025-09-09 | Completed
4 | Design and Requirement Analysis | 2025-09-21 | 2025-11-19 | Completed
4.1 | Requirement Gathering | 2025-09-21 | 2025-09-22 | Completed
4.2 | System Design | 2025-09-23 | 2025-10-05 | Completed
4.3 | Technology Stack Selection | 2025-10-05 | 2025-10-05 | Completed
4.4 | Finalizing Design Documents | 2025-11-19 | 2025-11-19 | Completed
5 | Project Development Plan | 2025-12-22 | - | Completed
5.1 | Disease Detection Module | 2025-12-22 | - | Completed
5.2 | Crop Recommendation Module | 2026-01-03 | 2026-01-06 | Completed
5.3 | News Module | 2026-01-21 | 2026-01-23 | Completed
6 | Testing and Debugging | 2026-01-29 | - | Ongoing
6.1 | Module Integration | 2026-01-29 | - | Completed
6.2 | Testing and Debugging | - | - | Ongoing
7 | Final Documentation and Presentation Preparation | - | - | Incomplete
7.1 | Final Presentation and Project Completion | - | - | Incomplete